## 📋 Overview
NurixSoft — Freelancing Services Platform
Company: NurixSoft · Release v1.0.0 · Released 2026-07-05 · Freelance Software Studio — Websites · Apps · UI/UX
Field | Details
Project | NurixSoft — Freelancing Services Platform + Client CRM (websites · apps · UI/UX for clients)
Company | NurixSoft
Contact | supportsujoydev@gmail.com · +91 8927673775
Package Name | com.sujoydev.app
Current Version | v1.0.0 (Initial Release)
Release Date | 2026-07-05 (Saturday) · first commit 12:32 · release verified 13:19
Repository | Monorepo: backend/ · admin/ · mobile/ · deployment/ · docs/
Backend Stack | Node.js + Express 4 + TypeScript + MongoDB (Mongoose 8) + JWT
Admin Stack | React 19 + Vite 8 + TypeScript + Material UI 9 + Redux Toolkit
Mobile Stack | React Native 0.86 + TypeScript + Redux Toolkit + React Navigation
Auth | Google Sign-In (verified on emulator) + JWT access/refresh + RBAC (user/admin/superadmin)
Deployment | Docker + docker-compose + Nginx · MongoDB Atlas · Play Store kit in docs/
OVERALL PROGRESS SUMMARY — v1.0.0
Area | Implemented | Pending | Completion
Backend API modules | 3 of 16 modules (Auth, Requests, Bugs) + health | 13 modules | ~30%
Database models | 7 of 19 (User, Admin, Session, ProjectRequest, BugReport, AuditLog, Counter) | 12 models | 37%
Admin dashboard | 4 pages (Login, Dashboard, Requests, Bugs) | 10 modules | ~30%
Mobile app | 13 of ~17 screens, Google Sign-In, tickets | Push, Settings, Notifications, offline queue | ~75%
Deployment & docs | Docker, Nginx, 6 docs, Play Store kit | CI/CD pipeline | ~90%
Roadmap phases | 10 of 15 phases complete (2 partial) | 5 phases | 67%

## 🗺 Roadmap Phases
Build Roadmap — 15 Phases
Phase-by-phase delivery plan with status and dates · v1.0.0 released 2026-07-05
Phase | Deliverable | Status | Start Date | End Date | Notes
1 | Monorepo structure, docs, roadmap | ✅ IMPLEMENTED | 2026-07-05 11:42 | 2026-07-05 12:32 | backend/, admin/, mobile/, deployment/, docs/ created
2 | Backend foundation — config, app/server, error handling, logger, utils | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 12:32 | env loader, database config, ApiError/ApiResponse, asyncHandler, logger, rate limiter
3 | Core Mongoose models (users, admins, sessions, requests, bugs, audit, counters) | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 12:32 | 7 models live; ticket counters for PRQ-/BUG- numbering
4 | Auth module — JWT + refresh rotation, Google Sign-In, RBAC, sessions, seed | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 13:19 | Real Google OAuth verified on emulator (commit 25e641a)
5 | Content APIs — projects, services, blogs, testimonials, reviews, favorites | 🔴 PENDING | — | — | Route stubs commented in routes/index.ts; mobile currently uses static portfolio.ts data
6 | Workflow APIs — project requests (tickets), bug reports | 🟡 PARTIAL | 2026-07-05 | 2026-07-05 12:32 | Create/track/list/status-update done; message threads & file uploads pending
7 | Notifications (FCM + Socket.IO), analytics, dashboard APIs, cron jobs | 🔴 PENDING | — | — | Needs Firebase project; sockets/ and jobs/ folders not yet created
8 | Admin dashboard — scaffold, auth, layout, theme, routing | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 12:32 | Vite + MUI 9 + Redux; DashboardLayout, theme.ts, admin JWT login
9 | Admin modules — requests + bugs management | 🟡 PARTIAL | 2026-07-05 | 2026-07-05 12:32 | Requests & Bugs pages done; Users/Projects/Blogs modules pending
10 | Admin analytics, notifications manager, settings, audit logs | 🔴 PENDING | — | — | AuditLog model exists in backend; no UI yet
11 | Mobile scaffold — navigation, redux, theme, API layer, offline queue | 🟡 PARTIAL | 2026-07-05 | 2026-07-05 12:32 | Navigation/redux/theme/API done; offline queue pending
12 | Mobile public screens — home, projects, services, blog, contact | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 12:44 | 11 public screens incl. detail screens
13 | Mobile auth + user features — requests, bugs, profile, favorites | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 13:19 | Login, ProjectRequest, BugReport, MyRequests (tracker), Profile, Favorites
14 | Push notifications (Firebase), deep links, polish | 🔴 PENDING | — | — | Blocked on Firebase project setup
15 | Deployment — Docker, Nginx, env, guides, Play Store release kit | ✅ IMPLEMENTED | 2026-07-05 | 2026-07-05 12:32 | Dockerfile, docker-compose, nginx conf, DEPLOYMENT.md, PLAYSTORE.md, privacy/terms

## ✅ Feature Tracker A-Z
Full Feature Tracker (A → Z)
Every planned feature across Backend · Admin · Mobile · DevOps with implementation status and dates
# | Module | Feature | Platform | Status | Date Done | Notes / Pending Work
1 | Auth | Google Sign-In (real OAuth token exchange) | Mobile+API | ✅ IMPLEMENTED | 2026-07-05 | Verified on emulator; web client ID configured
2 | Auth | Admin email/password login (JWT) | Admin+API | ✅ IMPLEMENTED | 2026-07-05 | POST /api/v1/auth/admin/login with rate limiting
3 | Auth | Refresh-token rotation | API | ✅ IMPLEMENTED | 2026-07-05 | POST /api/v1/auth/refresh + Session model
4 | Auth | Logout / session revoke | API | ✅ IMPLEMENTED | 2026-07-05 | POST /api/v1/auth/logout
5 | Auth | Role-based access (user/admin/superadmin) | API | ✅ IMPLEMENTED | 2026-07-05 | authorize() middleware on admin routes
6 | Auth | 2FA for admin | Admin | 🔴 PENDING | — | Planned ('2FA ready' in spec)
7 | Auth | Change password / delete account | Mobile | 🔴 PENDING | — | Profile actions not wired to API yet
8 | Project Requests | Submit request (budget, timeline, type, priority) | Mobile+API | ✅ IMPLEMENTED | 2026-07-05 | POST /api/v1/requests (optional auth)
9 | Project Requests | Auto ticket number PRQ-YYYYMM-XXXX | API | ✅ IMPLEMENTED | 2026-07-05 | Counter model generates sequence
10 | Project Requests | Public ticket tracking | Mobile+API | ✅ IMPLEMENTED | 2026-07-05 | GET /api/v1/requests/track/:ticket + MyRequestsScreen
11 | Project Requests | Admin list / filter / status update | Admin+API | ✅ IMPLEMENTED | 2026-07-05 | RequestsPage + PATCH status (admin only)
12 | Project Requests | File attachments on requests | Mobile+API | 🔴 PENDING | — | Multer + Cloudinary upload pipeline not built
13 | Project Requests | Message thread on a request | All | 🔴 PENDING | — | messages collection not created
14 | Bug Reports | Submit bug (title, priority, device info) | Mobile+API | ✅ IMPLEMENTED | 2026-07-05 | POST /api/v1/bugs + BugReportScreen
15 | Bug Reports | Auto ticket number BUG-YYYYMM-XXXX | API | ✅ IMPLEMENTED | 2026-07-05 | Counter-based
16 | Bug Reports | Admin bug triage (list, status) | Admin+API | ✅ IMPLEMENTED | 2026-07-05 | BugsPage + PATCH (admin only)
17 | Bug Reports | Screenshot attachment | Mobile | 🔴 PENDING | — | Needs upload module
18 | Bug Reports | Assign developer / close ticket flow | Admin | 🔴 PENDING | — | Spec item
19 | Content | Projects API (CRUD, categories, tech, images) | API | 🔴 PENDING | — | Phase 5 — projects collection
20 | Content | Services API (pricing, delivery time) | API | 🔴 PENDING | — | Phase 5
21 | Content | Blogs API (publish/draft, SEO, categories) | API | 🔴 PENDING | — | Phase 5
22 | Content | Testimonials API + approval flow | API | 🔴 PENDING | — | Phase 5
23 | Content | Reviews API | API | 🔴 PENDING | — | Phase 5
24 | Content | Favorites API (server-side sync) | API | 🔴 PENDING | — | Mobile favorites are local-only today
25 | Content | Portfolio content served from API | Mobile | 🔴 PENDING | — | Currently static in mobile/src/data/portfolio.ts
26 | Mobile | Home (hero, about, skills, stats, featured) | Mobile | ✅ IMPLEMENTED | 2026-07-05 | Agency hero with services CTA
27 | Mobile | Projects list + detail + search/filter | Mobile | ✅ IMPLEMENTED | 2026-07-05 | ProjectsScreen, ProjectDetailScreen
28 | Mobile | Services listing | Mobile | ✅ IMPLEMENTED | 2026-07-05 | ServicesScreen with ServiceCard
29 | Mobile | Blog list + detail | Mobile | ✅ IMPLEMENTED | 2026-07-05 | BlogScreen, BlogDetailScreen
30 | Mobile | Contact (call, WhatsApp, email, socials) | Mobile | ✅ IMPLEMENTED | 2026-07-05 | ContactScreen
31 | Mobile | Login screen (Google) | Mobile | ✅ IMPLEMENTED | 2026-07-05 | LoginScreen + googleAuth service
32 | Mobile | Profile screen | Mobile | ✅ IMPLEMENTED | 2026-07-05 | ProfileScreen
33 | Mobile | Favorites (save projects) | Mobile | ✅ IMPLEMENTED | 2026-07-05 | FavoritesScreen (local)
34 | Mobile | Request tracker (my tickets) | Mobile | ✅ IMPLEMENTED | 2026-07-05 | MyRequestsScreen + tickets service
35 | Mobile | Push notifications (FCM) | Mobile | 🔴 PENDING | — | Blocked on Firebase project
36 | Mobile | Notifications screen / inbox | Mobile | 🔴 PENDING | — | Planned with FCM
37 | Mobile | Settings screen | Mobile | 🔴 PENDING | — | Spec item
38 | Mobile | Offline cache / request queue | Mobile | 🔴 PENDING | — | Phase 11 leftover
39 | Mobile | Deep links | Mobile | 🔴 PENDING | — | Phase 14
40 | Mobile | Dark mode | Mobile | 🟡 PARTIAL | 2026-07-05 | Theme tokens exist; toggle/polish pending
41 | Notifications | FCM push (accepted/rejected/fixed/offer) | API | 🔴 PENDING | — | firebase-admin not configured
42 | Notifications | Socket.IO real-time events | API | 🔴 PENDING | — | sockets/ layer not created
43 | Notifications | Admin broadcast + scheduled sends | Admin | 🔴 PENDING | — | Notification manager UI pending
44 | Notifications | Email (Nodemailer/SMTP) | API | 🔴 PENDING | — | mailer config pending
45 | Analytics | Dashboard aggregate APIs | API | 🔴 PENDING | — | Counts currently derived from list endpoints
46 | Analytics | User growth / traffic / revenue charts | Admin | 🔴 PENDING | — | Charts library not yet added
47 | Analytics | Cron jobs (cleanup, rollups) | API | 🔴 PENDING | — | jobs/ folder not created
48 | Analytics | Audit log viewer | Admin | 🔴 PENDING | — | AuditLog model exists; UI pending
49 | DevOps | Dockerfile (backend) | DevOps | ✅ IMPLEMENTED | 2026-07-05 | backend/Dockerfile
50 | DevOps | docker-compose + Nginx reverse proxy | DevOps | ✅ IMPLEMENTED | 2026-07-05 | deployment/docker-compose.yml, nginx/nurixsoft.conf
51 | DevOps | Env templates (.env.example) | DevOps | ✅ IMPLEMENTED | 2026-07-05 | backend + admin
52 | DevOps | Docs: Architecture / Deployment / Google Auth / Play Store | Docs | ✅ IMPLEMENTED | 2026-07-05 | 6 markdown docs in docs/
53 | DevOps | Privacy Policy + Terms | Docs | ✅ IMPLEMENTED | 2026-07-05 | Required for Play Store data-safety form
54 | DevOps | CI/CD pipeline | DevOps | 🔴 PENDING | — | GitHub Actions not configured
55 | DevOps | Signed AAB + Play Store submission | DevOps | 🔴 PENDING | — | Checklist ready in PLAYSTORE.md

## 📊 Dashboard Features
Admin Dashboard — Feature Status
Everything the enterprise admin panel should have, and where it stands today
# | Dashboard Area | Feature | Status | Date Done | Notes
1 | Login & Security | Admin JWT login with refresh token | ✅ IMPLEMENTED | 2026-07-05 | LoginPage.tsx + rate-limited endpoint
2 | Login & Security | Role-based route guarding | ✅ IMPLEMENTED | 2026-07-05 | admin/superadmin roles enforced by API
3 | Login & Security | 2FA | 🔴 PENDING | — | Spec: '2FA ready'
4 | KPI Cards | Total Requests stat card | ✅ IMPLEMENTED | 2026-07-05 | DashboardPage.tsx
5 | KPI Cards | Pending Review stat card | ✅ IMPLEMENTED | 2026-07-05 | DashboardPage.tsx
6 | KPI Cards | Completed stat card | ✅ IMPLEMENTED | 2026-07-05 | DashboardPage.tsx
7 | KPI Cards | Open Bugs stat card | ✅ IMPLEMENTED | 2026-07-05 | DashboardPage.tsx
8 | KPI Cards | Total Users / Clients cards | 🔴 PENDING | — | Needs users list API
9 | KPI Cards | Revenue / Visitors / Downloads cards | 🔴 PENDING | — | Needs analytics module
10 | Charts | Monthly analytics charts (line/bar) | 🔴 PENDING | — | Chart library to be added
11 | Charts | Device / country / traffic breakdown | 🔴 PENDING | — | Analytics collection pending
12 | Charts | Recent activity feed | 🔴 PENDING | — | activity_logs collection pending
13 | Requests Module | Requests table with status chips | ✅ IMPLEMENTED | 2026-07-05 | RequestsPage.tsx (147 lines)
14 | Requests Module | Approve / reject / progress update | ✅ IMPLEMENTED | 2026-07-05 | PATCH /requests/:id status
15 | Requests Module | Search / advanced filter / export CSV / print | 🔴 PENDING | — | Spec items
16 | Bugs Module | Bug list with priority + status update | ✅ IMPLEMENTED | 2026-07-05 | BugsPage.tsx
17 | Bugs Module | Assign developer / export | 🔴 PENDING | — | Spec items
18 | User Management | View/search/ban/disable/export users | 🔴 PENDING | — | No users admin API yet
19 | Project Management | CRUD projects, categories, tags, images | 🔴 PENDING | — | Phase 5 backend first
20 | Service Management | CRUD services, pricing, featured flag | 🔴 PENDING | — | Phase 5
21 | Blog Management | CRUD blogs, publish/draft, SEO | 🔴 PENDING | — | Phase 5
22 | Messages | Inbox, reply, archive, attachments | 🔴 PENDING | — | messages collection pending
23 | Testimonials | Approve / reject / pin / feature | 🔴 PENDING | — | Phase 5
24 | Notifications | Send / broadcast / schedule / history | 🔴 PENDING | — | Needs FCM + notifications API
25 | Settings | General, SMTP, maintenance mode, API keys, backup | 🔴 PENDING | — | settings collection pending
26 | Audit Logs | Audit log viewer with actor/action/diff | 🔴 PENDING | — | Backend model exists; UI pending
27 | UX | Responsive layout + MUI theme | ✅ IMPLEMENTED | 2026-07-05 | DashboardLayout.tsx + theme.ts
28 | UX | Dark mode toggle | 🟡 PARTIAL | 2026-07-05 | Theme file present; toggle pending

## 🔌 API Endpoints
REST API — /api/v1
Implemented endpoints (live) and planned modules · uniform { success, message, data, meta } envelope
# | Method | Endpoint | Auth | Module | Status | Description
1 | GET | /api/v1/health | Public | System | ✅ IMPLEMENTED | Uptime, DB connection state, environment
2 | POST | /api/v1/auth/google | Public (rate-limited) | Auth | ✅ IMPLEMENTED | Google ID-token exchange → JWT pair
3 | POST | /api/v1/auth/admin/login | Public (rate-limited) | Auth | ✅ IMPLEMENTED | Admin email/password login
4 | POST | /api/v1/auth/refresh | Refresh token | Auth | ✅ IMPLEMENTED | Rotate refresh token, new access JWT
5 | POST | /api/v1/auth/logout | Optional | Auth | ✅ IMPLEMENTED | Revoke session
6 | POST | /api/v1/requests | Optional | Requests | ✅ IMPLEMENTED | Create project request, PRQ ticket
7 | GET | /api/v1/requests/track/:ticket | Public | Requests | ✅ IMPLEMENTED | Track request by ticket number
8 | GET | /api/v1/requests | Admin | Requests | ✅ IMPLEMENTED | List/filter all requests
9 | PATCH | /api/v1/requests/:id | Admin | Requests | ✅ IMPLEMENTED | Update status/progress
10 | POST | /api/v1/bugs | Optional | Bugs | ✅ IMPLEMENTED | Submit bug report, BUG ticket
11 | GET | /api/v1/bugs | Admin | Bugs | ✅ IMPLEMENTED | List/filter bug reports
12 | PATCH | /api/v1/bugs/:id | Admin | Bugs | ✅ IMPLEMENTED | Update bug status/priority
13 | CRUD | /api/v1/projects | Mixed | Projects | 🟣 PLANNED | Portfolio projects (commented stub in router)
14 | CRUD | /api/v1/services | Mixed | Services | 🟣 PLANNED | Service catalog + pricing
15 | CRUD | /api/v1/blogs | Mixed | Blogs | 🟣 PLANNED | Blog CMS
16 | CRUD | /api/v1/admin/* | Admin | Admin | 🟣 PLANNED | User management, settings, audit logs
17 | CRUD | /api/v1/testimonials · /reviews · /favorites | Mixed | Content | 🟣 PLANNED | Phase 5 content APIs
18 | CRUD | /api/v1/messages | Auth | Messages | 🟣 PLANNED | Client messaging threads
19 | CRUD | /api/v1/notifications | Mixed | Notifications | 🟣 PLANNED | FCM + in-app inbox
20 | GET | /api/v1/analytics/* · /dashboard/* | Admin | Analytics | 🟣 PLANNED | Aggregation-pipeline stats for dashboard
21 | POST | /api/v1/upload | Auth | Upload | 🟣 PLANNED | Multer + Cloudinary media upload
22 | GET | /api/v1/search | Public | Search | 🟣 PLANNED | Cross-collection search

## 🗄 Database Models
MongoDB Collections — 19 Planned
Mongoose models: 7 implemented · 12 pending · soft-delete + audit conventions
# | Collection | Status | Date Done | Purpose | Key Fields / Notes
1 | users | ✅ IMPLEMENTED | 2026-07-05 | End users (Google Sign-In) | email, googleId, role, avatar; soft delete
2 | admins | ✅ IMPLEMENTED | 2026-07-05 | Admin/superadmin accounts | bcrypt password hash, role
3 | sessions | ✅ IMPLEMENTED | 2026-07-05 | Refresh-token sessions | token hash, device, expiry, rotation
4 | project_requests | ✅ IMPLEMENTED | 2026-07-05 | Client project tickets | PRQ-YYYYMM-XXXX, budget, timeline, status
5 | bug_reports | ✅ IMPLEMENTED | 2026-07-05 | Bug tickets | BUG-YYYYMM-XXXX, priority, device info
6 | audit_logs | ✅ IMPLEMENTED | 2026-07-05 | Admin mutation trail | actor, action, target, diff, IP
7 | counters | ✅ IMPLEMENTED | 2026-07-05 | Atomic ticket sequences | per-month counter for PRQ/BUG
8 | projects | 🔴 PENDING | — | Portfolio projects | category, tech stack, images, links, featured
9 | services | 🔴 PENDING | — | Service catalog | price, delivery time, category, featured
10 | blogs | 🔴 PENDING | — | Blog CMS | publish/draft, SEO meta, tags, thumbnail
11 | messages | 🔴 PENDING | — | Client message threads | thread, attachments, read state
12 | notifications | 🔴 PENDING | — | Push/in-app notifications | target, type, schedule, read state
13 | testimonials | 🔴 PENDING | — | Client testimonials | approval flow, pinned, featured
14 | reviews | 🔴 PENDING | — | Project/service reviews | rating, moderation
15 | favorites | 🔴 PENDING | — | User saved items | user × project/service/blog
16 | analytics | 🔴 PENDING | — | Traffic & usage rollups | daily aggregates for dashboard charts
17 | settings | 🔴 PENDING | — | App settings | SMTP, maintenance mode, social links, API keys
18 | roles / permissions | 🔴 PENDING | — | Fine-grained RBAC | beyond the 3 built-in roles
19 | activity_logs | 🔴 PENDING | — | User activity feed | recent-activity widget source

## ⏳ Pending Backlog
Pending Work — Prioritized Backlog
Proposed release plan after v1.0.0 (target dates are proposals — adjust as needed)
# | Priority | Item | Area | Target Release | Target Date | Depends On
1 | P0 | Content APIs: projects, services, blogs (CRUD + public read) | Backend | v1.1.0 | 2026-07-19 | —
2 | P0 | Upload module (Multer + Cloudinary) for images/attachments | Backend | v1.1.0 | 2026-07-19 | Cloudinary account
3 | P0 | Mobile: switch static portfolio.ts to live content APIs | Mobile | v1.1.0 | 2026-07-19 | Content APIs
4 | P0 | Admin: Projects / Services / Blogs management pages | Admin | v1.1.0 | 2026-07-19 | Content APIs
5 | P1 | Testimonials, reviews, favorites APIs + moderation UI | Full stack | v1.1.0 | 2026-07-19 | Content APIs
6 | P1 | Admin: User management (search, ban, export) | Admin | v1.1.0 | 2026-07-19 | Users admin API
7 | P1 | FCM push notifications + notifications inbox | Full stack | v1.2.0 | 2026-08-02 | Firebase project setup
8 | P1 | Socket.IO real-time events (new ticket → admin) | Backend | v1.2.0 | 2026-08-02 | —
9 | P1 | Dashboard analytics APIs + charts (user growth, traffic) | Full stack | v1.2.0 | 2026-08-02 | analytics collection
10 | P2 | Messages module (threads, attachments, admin inbox) | Full stack | v1.2.0 | 2026-08-02 | Upload module
11 | P2 | Settings module (SMTP, maintenance mode, backups) | Full stack | v1.2.0 | 2026-08-02 | —
12 | P2 | Audit-log viewer + activity feed | Admin | v1.2.0 | 2026-08-02 | —
13 | P2 | Cron jobs: cleanup, analytics rollup, scheduled notifications | Backend | v1.2.0 | 2026-08-02 | —
14 | P2 | Email notifications (Nodemailer + SMTP) | Backend | v1.2.0 | 2026-08-02 | SMTP credentials
15 | P3 | Mobile: Settings screen, dark-mode toggle, offline queue | Mobile | v1.3.0 | 2026-08-16 | —
16 | P3 | Deep links + share links | Mobile | v1.3.0 | 2026-08-16 | —
17 | P3 | Admin 2FA + CSV export/print on all tables | Admin | v1.3.0 | 2026-08-16 | —
18 | P3 | CI/CD (GitHub Actions: lint, test, build, deploy) | DevOps | v1.3.0 | 2026-08-16 | —
19 | P3 | Signed AAB build + Play Store submission | DevOps | v1.3.0 | 2026-08-16 | Play Console account, FCM done

## 🚀 Release v1.0.0
Release Notes — v1.0.0 'Initial Release'
Company: NurixSoft · Released Saturday, 2026-07-05 · Build verified 13:19 IST
Time (2026-07-05) | Commit | Change | Type | Details
12:32 | a7d3029 | Initial release: NurixSoft freelancing platform v1.0.0 | 🎉 Release | Monorepo: backend, admin, mobile, deployment, docs — all Phase 1–4, 6, 8–9, 11–13, 15 work
12:44 | cb3f9b2 | Add brand assets | ✨ Feature | App imagery and content assets
12:44 | 6f68d4a | Remove Demo folder | 🧹 Chore | Assets consolidated into docs/ and mobile/src/assets
12:54 | 0b9cf7a | Wire real Google Sign-In with backend token exchange | ✨ Feature | Mobile googleAuth service ↔ POST /auth/google
13:19 | 25e641a | Configure Google OAuth Web client ID | ✅ Verified | Real Google Sign-In verified working on Android emulator
HIGHLIGHTS
✅ Working end-to-end | Google Sign-In → JWT session → submit project request / bug report → ticket number → track status → admin triages in dashboard
📱 Mobile app | 13 screens, React Native 0.86, Material Design, client-facing services content
🖥 Admin dashboard | React 19 + MUI 9: login, KPI cards, request & bug management
🔧 Backend | Express + TS: 12 live endpoints, 7 Mongoose models, JWT + refresh rotation, RBAC, rate limiting, central error handling, logging
🚢 Ship kit | Docker, docker-compose, Nginx, 6 docs incl. Play Store checklist, privacy policy, terms
⚠️ Known limitations | Portfolio content is static (no content APIs yet) · no push notifications · no analytics charts · uploads not supported yet